## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a user, I want to submit a support ticket so that my issue can be recorded | Must | Input Interface (basic form / planned UI) | Rahi (Team D) | Done
Sprint 1 | Sprint 1 | US02 | As a system, I want to preprocess ticket text (cleaning, normalization) for ML processing | Must | Dataset | Sameera / Dinesh (Team A) | Done
Sprint 1 | Sprint 1 | US03 | As a system, I want to classify tickets using TF-IDF and initial ML models | Must | Text preprocessing | Bhavya / Mounika(Team B) | Done
Sprint 2 | Sprint 2 | US04 | As a system, I want to extract entities using NER model (SpaCy + rules) | Must | NLP Model | Arya / Pratham (Team B) | Done
Sprint 2 | Sprint 2 | US05 | As a system, I want to generate structured ticket output (JSON format) | Must | Backend API | Tharun Sai | Done
Sprint 2 | Sprint 2 | US06 | As a system, I want to store tickets in database (SQLite) | Must | Database schema | Arya (Backend handled due to limited team availability) | Done
Sprint 3 | Sprint 3 | US07 | As an admin, I want to view all tickets in a dashboard | Should | Backend API | UI Team (Rahi, Asmita) | Done
Sprint 3 | Sprint 3 | US08 | As a system, I want to assign priority to tickets using rule-based logic | Must | Classification model | Arya /Thiruvikraman S.B | Done
Sprint 4 | Sprint 4 | US09 | As a user, I want to see confirmation after ticket submission | Could | Backend integration | UI Team | Done
Sprint 4 | Sprint 4 | US10 | As a team, we want to test the full system before deployment | Must | All modules | Team E + Arya | Done

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 162 | 9 | 9 | 10 | 11 | 10 | 12 | 12 | 9 | 11 | 11 | 15 | 19 | 17 | 7
SPRINT 1 BACKLOG
Sprint-1
US02 | T01 | Prepare ticket dataset | 2026-02-02 | 2026-02-03 | Sameera | Dataset collection | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Clean and preprocess dataset | 2026-02-04 | 2026-02-05 | Dinesh | Text preprocessing | Done | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Implement TF-IDF vectorization | 2026-02-06 | 2026-02-07 | Mounika | Feature extraction | Done | 6 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T04 | Train SVM classification model | 2026-02-08 | 2026-02-10 | Bhavya | Model training | Completed after iteration | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0
US04 | T05 | Implement NER model using spaCy | 2026-02-11 | 2026-02-12 | Arya | Entity extraction | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0
US05 | T06 | Develop backend ticket generation API | 2026-02-13 | 2026-02-14 | Tharun Sai | Backend development | Done | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0
US01 | T07 | Build ticket submission UI | 2026-02-14 | 2026-02-15 | Rahi Patel | UI development | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3
US03 | T08 | Integrate ML model with backend | 2026-02-15 | 2026-02-16 | Arya | System integration | In Progress | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4
Sprint-2
US03 | T09 | Improve SVM model accuracy | 2026-02-16 | 2026-02-18 | Arya | Hyperparameter tuning | Done | 7 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T10 | Expand NER training dataset | 2026-02-19 | 2026-02-20 | Bhavya | Dataset annotation | Done | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T11 | Train improved NER model | 2026-02-21 | 2026-02-22 | Arya | Model training | Completed after iteration | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T12 | Create ticket database schema | 2026-02-23 | 2026-02-24 | Tharun Sai | Database design | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US05 | T13 | Implement ticket storage logic | 2026-02-25 | 2026-02-26 | Arya | Backend coding | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0
US01 | T14 | Improve UI ticket form | 2026-02-27 | 2026-02-28 | Rahi Patel | UI enhancement | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0
US03 | T15 | Connect ML output to API | 2026-02-28 | 2026-03-01 | Arya | Integration | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
Sprint-3
US03 | T16 | Evaluate ML model performance | 2026-03-02 | 2026-03-03 | Arya | Accuracy testing | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T17 | Improve entity recognition | 2026-03-04 | 2026-03-05 | Bhavya | Model refinement | Completed after iteration | 6 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T18 | Implement ticket priority logic | 2026-03-06 | 2026-03-07 | Thiruvikraman S.B | Rule engine | Done | 5 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T19 | Create admin dashboard API | 2026-03-08 | 2026-03-10 | Tharun Sai | Backend development | Done | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US01 | T20 | UI ticket confirmation page | 2026-03-11 | 2026-03-12 | Asmita | UI development | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0
US03 | T21 | API-ML response validation | 2026-03-13 | 2026-03-14 | Arya | Integration testing | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
US05 | T22 | Ticket data validation logic | 2026-03-14 | 2026-03-15 | Tharun Sai | Backend validation | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0
Sprint-4
US03 | T23 | Final ML model optimization | 2026-03-16 | 2026-03-18 | Arya | Model tuning | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T24 | Final NER training update | 2026-03-19 | 2026-03-20 | Bhavya | Model improvement | Done | 5 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T25 | System integration testing | 2026-03-21 | 2026-03-22 | Ananya A M | Integration testing | Done | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T26 | Fix backend bugs | 2026-03-23 | 2026-03-24 | Tharun Sai | Bug fixing | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
US01 | T27 | UI bug fixing | 2026-03-23 | 2026-03-24 | Asmita | UI corrections | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
US05 | T28 | Final system testing | 2026-03-24 | 2026-03-25 | Team | QA testing | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
US05 | T29 | Documentation preparation | 2026-03-24 | 2026-03-25 | Ananya | Project documentation | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Dataset not finalized | Collected sample IT helpdesk tickets
Sprint 1 | Day 2 | Duplicate ticket data | Cleaned dataset and removed duplicates
Sprint 1 | Day 3 | Missing ticket labels | Added manual category annotations
Sprint 1 | Day 4 | Text preprocessing errors | Implemented tokenization and stopword removal
Sprint 1 | Day 5 | Dataset imbalance | Applied balancing techniques
Sprint 1 | Day 6 | Feature extraction confusion | Researched TF-IDF method
Sprint 1 | Day 7 | TF-IDF implementation error | Corrected vectorizer configuration
Sprint 1 | Day 8 | Model selection difficulty | Compared SVM and Naive Bayes
Sprint 1 | Day 9 | Low classification accuracy | Tuned hyperparameters
Sprint 1 | Day 10 | Feature mismatch error | Re-trained model with corrected features
Sprint 2 | Day 1 | NER model not identifying entities | Added new training examples
Sprint 2 | Day 2 | spaCy environment issue | Updated library dependencies
Sprint 2 | Day 3 | Entity extraction inconsistency | Adjusted training annotations
Sprint 2 | Day 4 | Ticket priority logic unclear | Designed rule-based priority engine
Sprint 2 | Day 5 | Integration between ML and backend | Created API interface
Sprint 2 | Day 6 | API response format mismatch | Updated JSON structure
Sprint 2 | Day 7 | Backend routing error | Fixed API endpoint configuration
Sprint 2 | Day 8 | Database schema incomplete | Designed ticket storage table
Sprint 2 | Day 9 | Ticket storage failure | Corrected database connection
Sprint 2 | Day 10 | Data validation issue | Implemented input validation
Sprint 3 | Day 1 | UI design not finalized | Designed ticket submission form
Sprint 3 | Day 2 | UI form validation issue | Added client-side validation
Sprint 3 | Day 3 | Frontend unable to call API | Updated fetch request logic
Sprint 3 | Day 4 | UI response display problem | Added confirmation message
Sprint 3 | Day 5 | Dashboard layout issue | Improved UI styling
Sprint 3 | Day 6 | Ticket display formatting error | Adjusted UI table structure
Sprint 3 | Day 7 | API latency | Optimized backend response
Sprint 3 | Day 8 | Model integration issue | Corrected model loading path
Sprint 3 | Day 9 | Incorrect ticket category prediction | Re-trained classification model
Sprint 3 | Day 10 | Entity extraction missing keywords | Updated NER dataset
Sprint 4 | Day 1 | System integration testing failures | Fixed module dependencies
Sprint 4 | Day 2 | Priority assignment inconsistency | Updated rule conditions
Sprint 4 | Day 3 | UI and backend mismatch | Standardized API response
Sprint 4 | Day 4 | Database record duplication | Added unique ticket ID
Sprint 4 | Day 5 | Performance issue under multiple requests | Optimized backend logic
Sprint 4 | Day 6 | Missing error handling | Implemented exception handling
Sprint 4 | Day 7 | Test case failures | Corrected classification logic
Sprint 4 | Day 8 | Minor UI bugs | Fixed layout alignment
Sprint 4 | Day 9 | Final testing issues | Completed debugging
Sprint 4 | Day 10 | Documentation updates pending | Finalized project documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-15 | Sameera | Start documenting dataset preparation steps | Stop working without dataset validation | Continue daily stand-up meetings | Created dataset documentation
2 | Sprint 1 | 2026-02-02 | 2026-02-15 | Dinesh | Start improving data preprocessing pipeline | Stop duplicate data entries | Continue data cleaning practices | Implemented preprocessing scripts
3 | Sprint 2 | 2026-02-16 | 2026-03-01 | Arya | Start hyperparameter tuning earlier | Stop training models without evaluation | Continue ML experimentation | Improved SVM model accuracy
4 | Sprint 2 | 2026-02-16 | 2026-03-01 | Bhavya | Start expanding NER training dataset | Stop ignoring entity extraction errors | Continue NER testing | Added more annotated samples
5 | Sprint 3 | 2026-03-02 | 2026-03-15 | Tharun Sai | Start backend API documentation | Stop unclear API response formats | Continue backend testing | Documented API endpoints
6 | Sprint 3 | 2026-03-02 | 2026-03-15 | Thiruvikraman S.B | Start integration testing earlier | Stop delaying bug fixes | Continue debugging process | Fixed API integration issues
7 | Sprint 4 | 2026-03-16 | 2026-03-25 | Asmita | Start UI testing before deployment | Stop pushing UI changes without testing | Continue UI improvements | Fixed layout issues
8 | Sprint 4 | 2026-03-16 | 2026-03-25 | Ananya | Start preparing documentation earlier | Stop last-minute documentation work | Continue maintaining project notes | Finalized project documentation